## Portfolio Cockpit
Executive Summary:
Portfolio: 13 624M total contract. Concentration: Gulf Coast 24%. Largest project: Jacksonville Terminal 924M.
NORTHBRIDGE | Portfolio Cockpit
Unit: M
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Cost & EAC Cockpit
Scope: | 4 | forecasted projects
Snapshot: | 2027-11
NORTHBRIDGE | Cost & EAC Cockpit
BAC
0,9B
EAC
0,8B
ETC
13,8M
EAC v. BAC
-95,2M
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Cash & Commitments Cockpit
NORTHBRIDGE | Cash & Commitments Cockpit
Committed Amount
9,9B
Invoiced Amount
5,8B
Paid Amount
4,7B
Open Commitments
5,1B

## Support Sheet
| BAC (Forecasted Projects) | EAC (Portfolio, Snapshot) | ETC (Forecasted Projects) | EAC v. BAC (Forecasted Projects) |  | # Forecasted Projects | Row Labels | Cash In | Cash Out
| 916525896.6559 | 821336211.3996 | 13814999.1473 | -95189685.2563 |  | 4 | 202703 | 13927902.334 | 7996880.1783
| 916525896.6559 | 821336211.3996 | 13814999.1473 | -95189685.2563 |  |  | 202704 | 28843321.542 | 9658242.7204
[6 empty] | Selected Snapshot Month | 202705 | 38755629.4086 | 14167642.4642
| Row Labels | EAC v. BAC (Forecasted Projects) |  |  |  | 202711 | 202706 | 39427269.8035 | 13866721.8529
| Small Projects Portfolio | -48828143.5084 |  |  |  | 2027-11 | 202707 | 45347792.3485 | 24378180.8783
| Delaware City Refinery | -26381680.0575 |  |  |  |  | 202708 | 51231235.8511 | 24377874.534
| Seattle Marine Terminal | -12179819.2272 |  |  |  |  | 202709 | 47622309.8937 | 22376755.779
| Other Projects Portfolio | -7800042.4633 |  |  |  |  | 202710 | 36723130.0702 | 22801193.8821
| Grand Total | -95189685.2563 |  |  |  |  | 202711 | 32688925.7329 | 28207906.0918
[7 empty] | Grand Total | 334567516.9845 | 167831398.3811
Row Labels | Total Contract (M) |  | Row Labels | Total Contract (M)
Jacksonville Terminal | 924.0997 |  | Gulf Coast | 3300.4125
Wood River Refinery | 884.1295 |  | Other | 2920.5918
Shared Services Upgrade | 883.3928 |  | South | 2342.1186
Beaumont Petrochem Plant | 767.5111 |  | Midwest | 1958.8599
Newark Tank Farm | 549.3523 |  | Northeast | 1643.3589
Corporate Modernization Program | 530.9267 |  | West | 1458.4291
Pascagoula Refinery | 526.5547 |  | Grand Total | 13623.7708
Small Projects Portfolio | 510.5185
Houston Marine Terminal | 498.0782
Salt Lake City Refinery | 492.8517
Grand Total | 6567.4153
Sum of committed_amount |  | Invoiced Amount |  | Paid Amount | Open Commitments
9879653454.9477 |  | 5776927502.1403 |  | 4731021322.1415 | 5148632132.8062
9879653454.9477 |  | 5776927502.1403 |  | 4731021322.1415 | 5148632132.8062
Row Labels | Committed | Paid
2022-08 | 5.6158 | 0.0088372
2022-09 | 127.5862 | 56.8207
2022-10 | 55.399 | 39.3469
2022-11 | 75.6093 | 25.9068
2022-12 | 130.2845 | 74.5905
2023-01 | 64.0377 | 33.2024
2023-02 | 123.2563 | 61.0433
2023-03 | 184.9088 | 95.4553
2023-04 | 222.9768 | 128.2014
2023-05 | 70.2121 | 49.6533
2023-06 | 174.3348 | 39.311
2023-07 | 261.736 | 126.2552
2023-08 | 230.7203 | 143.7039
2023-09 | 215.7802 | 48.2663
2023-10 | 432.0877 | 233.16
2023-11 | 469.2006 | 146.8843
2023-12 | 278.9302 | 105.6782
2024-01 | 338.92 | 170.1371
2024-02 | 324.9894 | 207.5806
2024-03 | 255.8649 | 141.7369
2024-04 | 318.4928 | 126.7588
2024-05 | 376.3 | 112.6427
2024-06 | 487.3771 | 301.0501
2024-07 | 131.1489 | 66.0531
2024-08 | 352.0117 | 159.9982
2024-09 | 432.0516 | 223.5653
2024-10 | 319.0439 | 117.3267
2024-11 | 246.2842 | 133.1316
2024-12 | 385.3704 | 200.6817
2025-01 | 207.5993 | 94.1881
2025-02 | 142.6247 | 58.7329
2025-03 | 250.9712 | 122.0927
2025-04 | 238.16 | 81.7892
2025-05 | 126.5448 | 86.5607
2025-06 | 331.0222 | 231.9436
2025-07 | 152.0208 | 57.9971
2025-08 | 112.5973 | 48.0059
2025-09 | 204.3714 | 99.0795
2025-10 | 189.6035 | 62.0685
2025-11 | 189.802 | 116.7697
2025-12 | 80.5727 | 35.5676
2026-01 | 67.7237 | 39.658
2026-02 | 32.5088 | 4.8633
2026-03 | 100.4676 | 46.2999
2026-04 | 83.7133 | 22.9373
2026-05 | 69.4314 | 47.1965
2026-06 | 51.2024 | 20.2671
2026-07 | 37.9655 | 13.2989
2026-08 | 14.7662 | 10.0507
2026-09 | 2.0885 | 1.0273
2026-10 | 55.2319 | 37.6758
2026-11 | 17.3167 | 10.2039
2026-12 | 16.7605 | 11.2956
2027-03 | 7.9229 | 3.1837
2027-05 | 2.1969 | 0.097614
2027-07 | 3.9359 | 0.019171
Grand Total | 9879.6535 | 4731.0213

## Model_Map
Table Name | Table Type (Dim/Fact) | Description | Grain (Fact only) | Primary Key | Foreign Keys | Relationships (From -> To) | Active? | Hide in Report View? | Notes
Controlling_TrainingModelCSV | Staging (Do not load) | Folder query listing all CSV files (staging only). | N/A | N/A | N/A | N/A | No | Yes | Keep as Connection Only. Do not add to Data Model.
dim_client | Dim | Client master list (who we work for). | N/A | client_key | — | dim_client[client_key] -> dim_project[client_key] (1:*) | Yes | No
dim_company | Dim | Company / legal entity (internal). | N/A | company_key | — | dim_company[company_key] -> dim_project[company_key] (1:*) | Yes | No
dim_region | Dim | USA regions (Gulf Coast, West, South, etc.). | N/A | region_key | — | dim_region[region_key] -> dim_project[region_key] (1:*) | Yes | No
dim_vendor | Dim | Vendor / subcontractor master list. | N/A | vendor_key | — | dim_vendor[vendor_key] -> fact_commitments[vendor_key] (1:*) | Yes | No
dim_date_month | Dim | Calendar month table for time intelligence. | N/A | month_key | — | dim_date_month[month_key] -> fact_project_month[month_key] (1:*) | Yes | No | Also used by multiple facts. Some relationships may be inactive (see facts).
dim_project | Dim | Project master (attributes: company, client, region). | N/A | project_id | company_key; client_key; region_key | dim_project[project_id] -> fact_project_month[project_id] (1:*) | Yes | No | This is the main hub for project-related slicing.
fact_project_month | Fact | Monthly actuals & performance (cost, revenue, progress, risk KPIs, etc.). | One row per Project per Month | project_id + month_key | project_id; month_key; company_key; client_key; region_key | dim_project[project_id] -> fact_project_month[project_id] (1:*); dim_date_month[month_key] -> fact_project_month[month_key] (1:*) | Yes | No | Prefer slicing Company/Client/Region via dim_project (avoid duplicate filter paths).
fact_baseline_month | Fact | Baseline / plan curve by month (planned progress/value). | One row per Project per Month | project_id + month_key | project_id; month_key | dim_project[project_id] -> fact_baseline_month[project_id] (1:*); dim_date_month[month_key] -> fact_baseline_month[month_key] (1:*) | Yes | No
fact_resource_plan_month | Fact | Resource plan by month (planned hours, cost, blended rate). | One row per Project per Month | project_id + month_key | project_id; month_key | dim_project[project_id] -> fact_resource_plan_month[project_id] (1:*); dim_date_month[month_key] -> fact_resource_plan_month[month_key] (1:*) | Yes | No
fact_project_contract | Fact | Project contract snapshot (contract value, COs, budget, planned margin). | One row per Project | project_id | project_id | dim_project[project_id] -> fact_project_contract[project_id] (1:*) | Yes | No
fact_commitments | Fact | Purchase orders & commitment lifecycle (committed, invoiced, paid, retainage, status). | One row per PO | po_id | project_id; vendor_key; po_issue_month_key; expected_payment_month_key | dim_project[project_id] -> fact_commitments[project_id] (1:*); dim_vendor[vendor_key] -> fact_commitments[vendor_key] (1:*); dim_date_month[month_key] -> fact_commitments[po_issue_month_key] (ACTIVE); dim_date_month[month_key] -> fact_commitments[expected_payment_month_key] (INACTIVE) | Yes | No | Second date relationship should be inactive; use USERELATIONSHIP in measures (or create a 2nd date table later).
fact_forecast_snapshot | Fact | Forecast over time with snapshotting (EAC cost, cash in/out) by snapshot month. | One row per Project per Month per Snapshot Month | project_id + month_key + snapshot_month_key | project_id; month_key; snapshot_month_key | dim_project[project_id] -> fact_forecast_snapshot[project_id] (1:*); dim_date_month[month_key] -> fact_forecast_snapshot[month_key] (ACTIVE); dim_date_month[month_key] -> fact_forecast_snapshot[snapshot_month_key] (INACTIVE) | Yes | No | For snapshot analysis you’ll use USERELATIONSHIP or later create a dedicated Snapshot Date dimension.
fact_commitments | Fact | Purchase order commitments (amounts, status, retainage) | One row per PO (po_id) | po_id | project_id; vendor_key; po_issue_month_key; expected_payment_month_key | dim_project[project_id] -> fact_commitments[project_id] (1:) ; dim_vendor[vendor_key] -> fact_commitments[vendor_key] (1:) ; dim_date_month[month_key] -> fact_commitments[po_issue_month_key] (1:*) | Yes | No | Keep only one active date relationship. Use po_issue as the default “time”. expected_payment can be added later as role-playing date or inactive.
fact_forecast_snapshot | Fact | Forecast versions (snapshot) with cash in/out and EAC | One row per snapshot_month_key + project_id + month_key | snapshot_month_key + project_id + month_key | project_id; month_key; snapshot_month_key | dim_project[project_id] -> fact_forecast_snapshot[project_id] (1:) ; dim_date_month[month_key] -> fact_forecast_snapshot[month_key] (1:) | Yes | No | This fact has two date roles: “forecast month” (month_key) and “snapshot month” (snapshot_month_key). For now keep month_key active. Later we can add a copy of dim_date_month as dim_snapshot_month to connect snapshot_month_key (then both can be active).